## Sheet1
Kent & Medway NHS and Social Care Partnership Trust
Performance in Initiating Clinical Research
April 2020 - March 2021
Quarter Reported | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Benchmark Met | Reason For Delay | Comments | Reasons for delay correspond to:
Q3 | 20/LO/1044 | 287176 | A Randomized, Double-Blind, Placebo-controlled Study Evaluating the Efficacy and Safety of SAGE-217 in the Treatment of Adults with Severe Postpartum Depression | No |  | 2020-06-18 | 2020-09-02 | 2020-11-25 | 2021-03-31 | 2021-03-31 | 2021-04-26 | No | No patients consented | Contracting delays during set-up due use of non-model commercial agreement. Challenging eligibility criteria required for study. | Both
Q3 | 19/LO/1667 | 271363 | Clinical and cost-effectiveness of a New psychological intervention to support Independence in Dementia (NIDUS) for family carers and people living with dementia in their own homes: A randomised controlled trial | Yes | 2021-01-27 | 2020-06-29 | 2020-09-18 | 2020-01-13 | 2020-09-18 | 2020-10-23 | 2020-11-10 | No | Staff availability issues | 70 day benchmark missed. Date site selected to confirmed 5 days over. Delays associated with staff availability | NHS Provider
Q4 | 20/LO/0034 | 274277 | APPLE-Tree programme for dementia prevention: pilot and RCT | Yes | 2021-07-12 | 2021-03-04 | 2021-03-25 | 2020-01-14 | 2021-04-15 | 2021-04-19 | 2021-06-16 | No | Staff availability issues | 70 day benchmark missed but date site selected to confirmed 25 calendar days. Delays were associated with obtaining information required to issue HR arrangements for external researchers and staff availability. | Both
Note on O5: Please use the free text comment box for more information about the trial. Character limit: 500